## Course Dev Timeline
COURSE DEVELOPMENT TIMELINE TRACKER
Free to use for your own course development. Please don't redistribute or resell as-is.
Turning complexity into clarity |  |  |  | cslearningsolutions.com
COURSE ID: |  | XX1234
COURSE TITLE: |  | COURSE NAME
SME NAME(S): |  | FIRST NAME LAST NAME
ID NAME: |  | FIRST NAME LAST NAME
STAKEHOLDER(S): |  | FIRST NAME LAST NAME
HOW TO USE THIS TEMPLATE • Cream-highlighted cells are yours to edit — course info, deliverables, dates, owners, and Y/N status. • White cells with dates in the weekly grid (from Week 2 on) calculate automatically; don't overwrite them. • "Development Completion Date", "Content Rec'd? Y/N," and "Owner" cells have dropdown menus — click the cell to select. • This is an 8-week development cycle. If your course moves faster or slower, adjust dates as needed and the formulas will still recalculate from there. Tracking more than one course? Copy the blank input row and paste it directly below — the formulas and dropdowns will carry over automatically. Add new rows above the "EXAMPLE" sections so your data stays together. A note on "Content": We use "Content" as a stand-in for whatever units your platform uses — modules (Canvas), content areas (Blackboard/Brightspace), lessons, units, etc. Adjust deliverable descriptions to match your platform's structure.
Report Date | Development Completion | Starting Date | Kickoff Mtg Date | Deliverables Due for Week 1 Mtg | Owner | Week 1 Meeting Date | Content Rec'd? Y/N | Deliverables Due for Week 2 Mtg | Owner | Week 2 Meeting Date | Content Rec'd? Y/N | Deliverables Due for Week 3 Mtg | Owner | Week 3 Meeting Date | Content Rec'd? Y/N | Deliverables Due for Week 4 Mtg | Owner | Week 4 Meeting Date | Content Rec'd? Y/N | Deliverables Due for Week 5 Mtg | Owner | Week 5 Meeting Date | Content Rec'd? Y/N | Deliverables Due for Week 6 Mtg | Owner | Week 6 Meeting Date | Content Rec'd? Y/N | Deliverables Due for Week 7 Mtg | Owner | Week 7 Meeting Date | Content Rec'd? Y/N | Deliverables Due for Week 8 Mtg | Owner | Week 8 Meeting Date | Content Rec'd? Y/N | This Week's Comments | Overall Status
| Not Started |  |  | Content TBD |  |  |  | Content TBD |  |  |  | Content TBD |  |  |  | Content TBD |  |  |  | Content TBD |  |  |  | Content TBD |  |  |  | Content TBD |  |  |  | Content TBD |  |  |  |  | ON TRACK
EXAMPLE — Course Development On-Time
Report Date | Development Completion | Starting Date | Kickoff Mtg Date | Deliverables Due for Week 1 Mtg | Owner | Week 1 Meeting Date | Content Rec'd? Y/N | Deliverables Due for Week 2 Mtg | Owner | Week 2 Meeting Date | Content Rec'd? Y/N | Deliverables Due for Week 3 Mtg | Owner | Week 3 Meeting Date | Content Rec'd? Y/N | Deliverables Due for Week 4 Mtg | Owner | Week 4 Meeting Date | Content Rec'd? Y/N | Deliverables Due for Week 5 Mtg | Owner | Week 5 Meeting Date | Content Rec'd? Y/N | Deliverables Due for Week 6 Mtg | Owner | Week 6 Meeting Date | Content Rec'd? Y/N | Deliverables Due for Week 7 Mtg | Owner | Week 7 Meeting Date | Content Rec'd? Y/N | Deliverables Due for Week 8 Mtg | Owner | Week 8 Meeting Date | Content Rec'd? Y/N | This Week's Comments | Overall Status
2026-05-20 | 50% | 2026-05-15 | 2026-05-20 | Modules 1-2 | SME | 2026-05-27 | YES | Modules 3-4 | SME | 2026-06-03 | YES | Modules 5-6 | SME | 2026-06-10 | YES | Modules 7-8 | SME | 2026-06-17 | YES | Modules 9-10 | SME | 2026-06-24 | YES | Modules 11-12 | SME | 2026-07-01 | YES | Modules 13-14 | SME | 2026-07-08 | YES | Review course and send edits to ID for final mtg | SME | 2026-07-15 | YES | Week 1 mtg content on track | ON TRACK
EXAMPLE — Course Development Delayed
Report Date | Development Completion | Starting Date | Kickoff Mtg Date | Deliverables Due for Week 1 Mtg | Owner | Week 1 Meeting Date | Content Rec'd? Y/N | Deliverables Due for Week 2 Mtg | Owner | Week 2 Meeting Date | Content Rec'd? Y/N | Deliverables Due for Week 3 Mtg | Owner | Week 3 Meeting Date | Content Rec'd? Y/N | Deliverables Due for Week 4 Mtg | Owner | Week 4 Meeting Date | Content Rec'd? Y/N | Deliverables Due for Week 5 Mtg | Owner | Week 5 Meeting Date | Content Rec'd? Y/N | Deliverables Due for Week 6 Mtg | Owner | Week 6 Meeting Date | Content Rec'd? Y/N | Deliverables Due for Week 7 Mtg | Owner | Week 7 Meeting Date | Content Rec'd? Y/N | Deliverables Due for Week 8 Mtg | Owner | Week 8 Meeting Date | Content Rec'd? Y/N | This Week's Comments | Overall Status
2026-01-21 | < 25% | 2026-07-01 | 2026-07-07 | Modules 1-2 | SME | 2026-07-14 | NO | Modules 3-4 | SME | 2026-07-28 | YES | Modules 5-6 | ID | 2026-08-04 | NO | Modules 7-8 | SME | 2026-08-18 | YES | Modules 9-10 | Stakeholder | 2026-08-25 | YES | Modules 11-12 | SME | 2026-09-01 | NO | Modules 13-14 | SME | 2026-09-15 | YES | Review course and send edits to ID for final mtg | SME | 2026-09-22 | YES | Week 1 - SME turned in content late; final timeline shifted two weeks; Week 3 - SME turned in content late; final timeline shifted two weeks. | DELAYED
© 2026 Complete Learning Solutions LLC · cslearningsolutions.com · Course Development Timeline Tracker
Formulas:
Week 2 Meeting Date = IF([Week 1 Meeting Date]="","",IF([Content Rec'd? Y/N]="NO",[Week 1 Meeting Date]+14,[Week 1 Meeting Date]+7))
Week 3 Meeting Date = IF([Week 2 Meeting Date]="","",IF([Content Rec'd? Y/N]="NO",[Week 2 Meeting Date]+14,[Week 2 Meeting Date]+7))
Week 4 Meeting Date = IF([Week 3 Meeting Date]="","",IF([Content Rec'd? Y/N]="NO",[Week 3 Meeting Date]+14,[Week 3 Meeting Date]+7))
Week 5 Meeting Date = IF([Week 4 Meeting Date]="","",IF([Content Rec'd? Y/N]="NO",[Week 4 Meeting Date]+14,[Week 4 Meeting Date]+7))
Week 6 Meeting Date = IF([Week 5 Meeting Date]="","",IF([Content Rec'd? Y/N]="NO",[Week 5 Meeting Date]+14,[Week 5 Meeting Date]+7))
Week 7 Meeting Date = IF([Week 6 Meeting Date]="","",IF([Content Rec'd? Y/N]="NO",[Week 6 Meeting Date]+14,[Week 6 Meeting Date]+7))
Week 8 Meeting Date = IF([Week 7 Meeting Date]="","",IF([Content Rec'd? Y/N]="NO",[Week 7 Meeting Date]+14,[Week 7 Meeting Date]+7))